## plan-timetable (1)
reference | plan | plan-event | event-date | actual-date | entry-date | notes
dartmoor-national-park-authority-local-plan-2018-plan-adopted | dartmoor-national-park-authority-local-plan-2018 | plan-adopted |  |  | 2026-03-30
dartmoor-national-park-authority-local-plan-2018-reg-19-publication-local-plan-published | dartmoor-national-park-authority-local-plan-2018 | reg-19-publication-local-plan-published |  |  | 2026-03-30
dartmoor-national-park-authority-local-plan-2018-planning-inspectorate-found-sound | dartmoor-national-park-authority-local-plan-2018 | planning-inspectorate-found-sound |  |  | 2026-03-30
dartmoor-national-park-authority-local-plan-2018-submit-plan-for-examination | dartmoor-national-park-authority-local-plan-2018 | submit-plan-for-examination |  |  | 2026-03-30
dartmoor-national-park-authority-local-plan-2026-publish-notice-intention-commence | dartmoor-national-park-authority-local-plan-2026 | publish-notice-intention-commence | 2026-06-30 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-scoping-consultation-start | dartmoor-national-park-authority-local-plan-2026 | scoping-consultation-start | 2026-07-13 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-scoping-consultation-end | dartmoor-national-park-authority-local-plan-2026 | scoping-consultation-end | 2026-08-23 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-gateway-1-self-assessment | dartmoor-national-park-authority-local-plan-2026 | gateway-1-self-assessment | 2026-10-30 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-plan-content-evidence-consultation-start | dartmoor-national-park-authority-local-plan-2026 | plan-content-evidence-consultation-start | 2027-06-07 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-plan-content-evidence-consultation-end | dartmoor-national-park-authority-local-plan-2026 | plan-content-evidence-consultation-end | 2027-07-18 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-gateway-2-advice-sought | dartmoor-national-park-authority-local-plan-2026 | gateway-2-advice-sought | 2027-11-01 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-gateway-2-advice-published | dartmoor-national-park-authority-local-plan-2026 | gateway-2-advice-published | 2027-12-01 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-proposed-plan-consultation-start | dartmoor-national-park-authority-local-plan-2026 | proposed-plan-consultation-start | 2028-08-01 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-proposed-plan-consultation-end | dartmoor-national-park-authority-local-plan-2026 | proposed-plan-consultation-end | 2028-07-02 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-gateway-3-advice-sought | dartmoor-national-park-authority-local-plan-2026 | gateway-3-advice-sought | 2028-08-21 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-gateway-3-advice-published | dartmoor-national-park-authority-local-plan-2026 | gateway-3-advice-published | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-gateway-3-further-advice-sought | dartmoor-national-park-authority-local-plan-2026 | gateway-3-further-advice-sought | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-gateway-3-repeat-advice-published | dartmoor-national-park-authority-local-plan-2026 | gateway-3-repeat-advice-published | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-examination-submitted | dartmoor-national-park-authority-local-plan-2026 | examination-submitted | 2028-09-29 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-examination-recommendations-published | dartmoor-national-park-authority-local-plan-2026 | examination-recommendations-published | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-main-modification-consultation-start | dartmoor-national-park-authority-local-plan-2026 | main-modification-consultation-start | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-main-modification-consultation-end | dartmoor-national-park-authority-local-plan-2026 | main-modification-consultation-end | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-examination-pause-start | dartmoor-national-park-authority-local-plan-2026 | examination-pause-start | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-examination-pause-end | dartmoor-national-park-authority-local-plan-2026 | examination-pause-end | dependent on outcome from Inspector. |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-adopted | dartmoor-national-park-authority-local-plan-2026 | adopted | 30/04/2029 |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-additional-consultation-start | dartmoor-national-park-authority-local-plan-2026 | additional-consultation-start | optional |  | 2026-06-29
dartmoor-national-park-authority-local-plan-2026-additional-consultation-end | dartmoor-national-park-authority-local-plan-2026 | additional-consultation-end | optional |  | 2026-06-29